## Slide 1: Goals for Thesis
Predict age and dyslexia from EEG data
Compare deep learning models on EEG classification tasks
Explain and visualise the reasoning behind the models
Make the code reproducable for other projects and datasets

## Slide 2: Progress
Code for thesis:
Load data/metadata/events ePOD dataset
Created dummy data
Trained simple deep learning model
Learning to work in team
GitHub + Kanban

## Slide 3
2018
2019
Today
Jun
Jul
Aug
Sep
Oct
Nov
Start
Main Thesis
May 1
Finish preprocessing pipeline
Aug1
8 days
24 days
MAIN GOALS:
1: Reproduce age prediction results
2. Predict familial dyslexia
3: Use state-of-the-art models
4. Make DL models explainable
5. Make code reusable
34 days
23 days
Create preprocessing data pipeline
Research and implement multiple models:
FCNN/CNN/RNN/
Transformer
Train on real EEG data
35 days
31 days
End Date
Nov 14
PowerPoint Gantt Chart
May
Load data/metadata/events ePOD dataset
Create dummy data generator
Create simple DL classificication model for EEG data
Learn about GitHub/Kanban/Surf
This Meeting
June 8
Predict age on DDP and ePOD dataset
Make code reproducable (the code should at minimum be able to process DDP and ePOD dataset)
Implement most promising DL models
Model evaluation
Finish age
prediction model
Finish dyslexia prediction model
Make system to evaluate EEG DL classification/ regression models on:
1. learning speed
2. maximum performance on classification tasks
3. explainability.
Train the models to predict the parental risk of dyslexia.
Make models explainable
(e.g. by by comparing predicted signals from different categories,
or by visualising the model’s attention to individual data segments)
Start writing thesis.
Write thesis
Wrap up unfinished tasks
Clean up code for easy reusability
Finish Thesis
Jul 1
Sep 1
Oct 1